## Data
Queue Number | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim Interconnection Service Agreement | Interim/Interconnection Service Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Queue Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Projected In Service Date | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Queue | Sliding Queue
G00_MTX2B | Keeney-Steele 230kV |  | DC | Unknown | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR/FTR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g00_mtx2b_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2001 | N/A | N/A |  |  |  | 1/1/2005 |  |  | S | No
G00_MTX2C | Vienna-Piney Grove 230kV |  | MD | Dorchester | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR/FTR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g00_mtx2c_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2001 | N/A | N/A |  |  |  | 1/1/2005 |  |  | S | No
G00_MTX3 | Erie West 345kV |  | PA | Erie | Withdrawn | Unknown | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | C/TIR/1000 F/TW | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g00_mtx3_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g00_mtx3_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2001 | N/A | N/A |  | 7/10/2003 |  | 6/30/2004 |  |  | S | No
G32_MTX6 | Linden 230kV, 138kV |  | NJ | Union | Withdrawn | PSEG | 365 | 365 | 365 |  | Capacity | Merchant Transmission |  | DC | R/TIR/365 F/TWR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g32_mtx6_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g32_mtx6_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/3/2001 | N/A | N/A |  | 8/12/2004 |  | 12/31/2005 |  |  | S | No
H05_MTX9 |  |  | MD | Calvert | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2001 | N/A | N/A | [6 empty] | S | No
I07_MTX8 |  |  | NJ | Middlesex | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2001 | N/A | N/A | [6 empty] | S | No
J01_MTX | Hope Creek 500kV Cedar Creek 230kV |  | DC | Unknown | Withdrawn | PSEG | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/j01_mtx_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2002 | N/A | N/A |  | 12/5/2003 |  |  |  |  | S | No
J02_MTX11 | Vienna 230kV - Chalk Point 230kV |  | MD | Dorchester | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2003 | N/A | N/A |  | 4/28/2005 |  | 1/1/2006 |  |  | S | No
J08_MTX14 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | Unknown | 80 | 80 | 80 |  | Capacity | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2003 | N/A | N/A |  | 4/22/2003 |  | 6/30/2005 |  |  | S | No
J08_MTX15 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | Unknown | 790 |  |  |  | Energy | Merchant Transmission |  | DC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2003 | N/A | N/A |  | 9/26/2003 |  | 6/30/2006 |  |  | S | No
L15 | Buffalo Road-Carry East to NY |  | NY | Chautauqua | Withdrawn | PENELEC | 34 | 34 | 34 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/l15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2004 | N/A | N/A |  | 10/18/2004 | Customer Milestone Not Met | 11/1/2005 |  |  | S | No
M09 | Island Road |  | PA | Philadelphia | Withdrawn | PECO | 50 | 50 |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/m09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/m09_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2004 | N/A | N/A |  |  | Customer Initiated Withdrawal | 8/31/2007 |  |  | S | No
M10 | Vienna/Chalk Point |  | MD | Prince George's | Withdrawn | PEPCO | 400 | 400 | 400 |  | Capacity | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2004 | N/A | N/A |  | 10/28/2004 | Customer Initiated Withdrawal | 1/1/2008 |  |  | S | No
M16 | Peach Bottom T1 |  | PA | York | Withdrawn | PECO | 0 |  |  |  | Energy | Merchant Transmission | Nuclear | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2004 | N/A | N/A |  | 12/7/2004 | Customer Initiated Withdrawal | 11/1/2005 |  |  | S | No
O06 | Ft. Martin Pruntytown |  | WV | Taylor | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o06_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2005 | N/A | N/A |  | 6/13/2006 |  | 6/1/2008 |  |  | S | No
O08 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2005 | N/A | N/A | [6 empty] | S | No
O13 | Linden - Harbor Cable II |  | NJ | Union | Withdrawn | PSEG | 520 |  |  |  | Energy | Merchant Transmission |  | DC | F/TWR/520 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 2/1/2008 |  |  | S | No
O14 | Black Oak - Bedinton RTU |  | MD | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o14_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/5/2005 | N/A | N/A |  | 8/14/2006 | Customer Milestone Not Met |  |  |  | S | No
O15 | Black Oak - Hatfield Wave Trap |  | PA | Greene | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o15_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/6/2005 | N/A | N/A |  | 10/3/2006 | Customer Initiated Withdrawal |  |  |  | S | No
O45 | Grassy Falls | University Park | WV | Greenbrier | Withdrawn | APS | 143 | 143 | 143 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o45_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o45_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/o45_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2005 | N/A | N/A |  | 1/6/2009 | Customer Initiated Withdrawal | 11/1/2007 |  |  | S | No
O67 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A | [6 empty] | S | No
P12 | Cheswick - Springdale 138kV |  | PA | Allegheny | Withdrawn | DL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2005 | N/A | N/A |  | 4/28/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P29 | Hunterstown 500/230kV |  | PA | Adams | Withdrawn | ME | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p29_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/22/2005 | N/A | N/A |  | 5/17/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P45B | Mt. Storm 500kV |  | WV | Unknown | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2006 | N/A | N/A |  | 10/3/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P56 | Elrama-Mitchell 138kV |  | PA | Allegheny | Withdrawn | DL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p56_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/p56_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 8/21/2007 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
P57 | Charleroi - Mitchell 138kV |  | PA | Allegheny | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p57_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 8/28/2006 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
Q21 | Lewistown-Juniata 230kV |  | PA | Cambria | Withdrawn | PENELEC | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2006 | N/A | N/A |  | 5/4/2006 | Customer Initiated Withdrawal | 12/15/2006 |  |  | S | No
Q38 | C2 Tap - Mt. Union 46kV |  | PA | Cambria | Withdrawn | PENELEC | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/q38_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/q38_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/4/2006 | N/A | N/A |  | 12/5/2007 | Customer Milestone Not Met | 12/15/2007 | 12/15/2007 |  | S | No
Q75 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 1000 | 1000 | 685 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/q75_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/q75_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 12/2/2008 |  | 6/1/2010 |  |  | S | No
Q87 | Quad Cities 345kV |  | IL | Whiteside | Withdrawn | ComEd | 0 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 1/22/2007 | Customer Milestone Not Met | 1/1/2008 |  |  | S | No
Q88 | Black Oak SVC |  | WV | Berkeley | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/q88_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 10/31/2006 | Customer Initiated Withdrawal | 6/1/2008 |  |  | S | No
R25 | Dickerson - Pleasant View 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2006 | N/A | N/A |  | 1/30/2007 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
R34 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2006 | N/A | N/A | [6 empty] | S | No
R47 |  |  | PA | Lancaster | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2006 | N/A | N/A | [6 empty] | S | No
R75 | Mitchell - Shepler Hill 138kV |  | PA | Allegheny | Withdrawn | APS | 242 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/r75_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/r75_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2007 | N/A | N/A |  | 5/3/2007 | Customer Milestone Not Met | 1/1/2008 |  |  | S | No
R90 | Dickerson-Pleasant View 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 14 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/r90_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/r90_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 1/30/2007 | N/A | N/A |  | 7/3/2007 | Customer Milestone Not Met | 6/1/2007 |  |  | S | No
S104 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 5/14/2008 | Customer Milestone Not Met | 6/1/2011 |  |  | S | No
S119 | Lexington-Dooms 500kV |  | VA | Augusta | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s119_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 1/16/2008 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
S120 | Bristers-Ox 500kV |  | VA | Fauquier | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s120_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 1/16/2008 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
S15 | Burches Hill 500-230kV |  | MD | Prince George's | Withdrawn | PEPCO | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s15_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 8/7/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
S16 | Gilbert-Glen Gardner 230kV |  | NJ | Hunterdon | Withdrawn | JCPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s16_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 12/4/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
S57 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1500 |  |  |  | Energy | Merchant Transmission | Wind | DC | F/TIR 300/NF/TIR 1200 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s57_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s57_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/11/2007 | N/A | N/A |  | 4/10/2017 |  | 12/31/2020 | 12/31/2020 |  | S | No
S58 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1600 | 0 | 0 |  | Energy | Merchant Transmission | Wind | DC | F/TIR 400/NF/TIR 1200 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s58_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s58_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/11/2007 | N/A | N/A |  | 1/19/2018 |  | 12/31/2020 | 12/31/2020 |  | S | No
S68 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 660 | 660 | 0 |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s68_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2007 | N/A | N/A |  | 4/23/2008 | Customer Initiated Withdrawal | 12/31/2007 |  |  | S | No
T112 | Morrisville-Loudoun 500kV |  | VA | Fauquier | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/t112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/t112_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/12/2007 | N/A | N/A |  | 7/28/2009 | Customer Initiated Withdrawal | 10/1/2010 | 10/1/2010 |  | S | No
T132 | Cloverdale-Lexington 500kV |  | VA | Botetourt | Withdrawn | AEP | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/9/2008 | N/A | N/A |  | 12/9/2009 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
T145 | AP South 500kV |  | N/A | N/A | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2008 | N/A | N/A |  | 12/29/2009 | Customer Milestone Not Met | 12/31/2008 |  |  | S | No
T47 | Mt. Storm-Doubs 500kV |  | VA | Unknown | Withdrawn | Dominion | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/t47_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2007 | N/A | N/A |  | 12/17/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
U2-046 | Roseland 500kV |  | NJ | Essex | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 660/TWR 670 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2046_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2008 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 12/1/2013 |  |  | S | No
U2-047 | Deans 500kV |  | NJ | Unknown | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 660/TWR 672 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2008 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 12/1/2013 |  |  | S | No
U2-086 | Airydale 500kV |  | PA | Huntingdon | Withdrawn | PENELEC | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 9/17/2010 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-087 | Juniata 500 MVAR SVC |  | PA | Dauphin | Withdrawn | PPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/u2087_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 7/6/2012 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-088 | Meadow Brook 500kV |  | VA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 1/5/2012 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-089 | Kemptown 500kV |  | PA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 9/16/2008 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-100 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 800 |  |  |  | Energy | Merchant Transmission |  | AC | NF/TWR 800 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 4/26/2011 | Customer Initiated Withdrawal | 12/1/2011 |  |  | S | No
U3-005 | Meadow Brook |  | VA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u3005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u3005_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2008 | N/A | N/A |  | 2/1/2012 | Customer Initiated Withdrawal | 12/31/2008 |  |  | S | No
U3-026 | Collins |  | IL | Grundy | Withdrawn | ComEd | 0 |  |  |  | Energy | Merchant Transmission | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u3026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u3026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/9/2008 | N/A | N/A |  | 4/10/2017 |  | 12/31/2020 | 12/31/2020 |  | S | No
U4-018 | Bedington-Harmony Jct 138kV |  | WV | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u4018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2008 | N/A | N/A |  | 3/30/2010 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
U4-031 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2008 | N/A | N/A |  | 4/30/2009 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
V1-005 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v1005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v1005_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/12/2009 | N/A | N/A |  | 3/16/2010 | Customer Initiated Withdrawal | 1/1/2010 |  |  | S | No
V1-006 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2009 | N/A | N/A |  | 4/30/2009 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
V2-007 | Bedington-Harmony Jct 138kV |  | MD | Allegany | Withdrawn | APS |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v2007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v2007_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2009 | N/A | N/A |  | 2/10/2012 | Customer Initiated Withdrawal | 6/1/2010 |  |  | S | No
V2-019A | Dumont 765kV |  | IN | Unknown | Withdrawn | AEP | 7900 |  |  |  | Energy | Merchant Transmission |  | DC | F/NF TIR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v2019a_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2009 | N/A | N/A |  | 5/25/2010 | Customer Milestone Not Met | 5/1/2015 |  |  | S | No
V3-020 | Mt. Storm-Valley 115kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-021 | Mt. Storm-Doubs 500kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-022 | 502 Junction-Meadowbrook 500kV |  | WV | Hardy | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-023 | Alburtis-Hosensack 500kV |  | PA | Unknown | Withdrawn | PPL | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A |  | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-026 | Larrabee 230kV |  | NJ | Ocean | Withdrawn | JCPL | 550 |  |  |  | Energy | Merchant Transmission |  | DC | F/550 TIR/550 TWR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v3026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 8/24/2012 | Customer Initiated Withdrawal | 1/1/2013 |  |  | S | No
V3-046 | Conemaugh-Juniata 500kV |  | PA | Cambria | Withdrawn | PENELEC | 741 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v3046_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/v3_046_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2009 | N/A | N/A |  | 12/16/2014 | Customer Milestone Not Met | 7/1/2012 |  |  | S | No
V4-026 | Pontiac-Dumont 345kV |  | IL | Unknown | Withdrawn | AEP | 3000 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v4026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2009 | N/A | N/A |  | 1/3/2013 | Customer Milestone Not Met | 6/30/2014 |  |  | S | No
V4-058 | Collins HVDC |  | SD | Hand | Withdrawn | ComEd | 3500 |  |  |  | Energy | Merchant Transmission |  |  | F/1650/NF/1850 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v4058_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2010 | N/A | N/A |  | 9/14/2012 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
W1-002 | Tiltonsville-Windsor 138kV |  | OH | Jefferson | Withdrawn | AEP | 98 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1002_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2010 | N/A | N/A |  | 7/20/2012 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
W1-025 | Mt. Storm-Valley 500kV |  | WV | Unknown | Withdrawn | Dominion | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1025_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-026 | Mt. Storm-Doubs 500kV |  | WV | Unknown | Withdrawn | Dominion | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-027 | 502 Junction-Meadowbrook 500kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-028 | Alburtis-Hosensack |  | PA | Unknown | Withdrawn | PPL | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 11/18/2010 | Customer Milestone Not Met | 12/31/2013 |  |  | S | No
W1-053 | Pleasant View 500kV |  | VA | Arlington | Withdrawn | Dominion | 229 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2010 | N/A | N/A |  | 9/14/2010 | Customer Milestone Not Met | 6/1/2013 |  |  | S | No
W1-061 | Brambleton |  | VA | Loudoun | Withdrawn | Dominion | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2010 | N/A | N/A |  | 5/25/2010 |  | 6/1/2013 |  |  | S | No
W1-063 | Branchburg-Elroy 500kV |  | NJ | Somerset | Withdrawn | PSEG | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1063_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2010 | N/A | N/A |  | 6/10/2010 |  | 6/1/2011 |  |  | S | No
W2-008 | Tiltonsville-Windsor 138kV |  | OH | Jefferson | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2010 | N/A | N/A |  | 4/12/2012 | Customer Initiated Withdrawal | 6/1/2011 |  |  | S | No
W2-013 | Branchburg-Elroy 500kV |  | NJ | Unknown | Withdrawn | PSEG | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w2013_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/w2013_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/24/2010 | N/A | N/A |  | 7/21/2014 | Customer Milestone Not Met | 6/1/2012 |  |  | S | No
W2-043 | Albright-Snowy Creek 138kV |  | WV | Preston | Withdrawn | APS | 101 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w2043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w2043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 1/17/2012 | Customer Milestone Not Met | 4/1/2011 |  |  | S | No
W3-027 | Meadowbrook 500kV |  | VA | Frederick | Withdrawn | APS | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w3027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w3027_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/w3027_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 12/9/2013 | Customer Initiated Withdrawal | 6/1/2011 |  |  | S | No
W3-062 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2010 | N/A | N/A | [6 empty] | S | No
W3-122 | Brandon Shores-Riverside 230kV |  | MD | Unknown | Withdrawn | BGE | 236 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w3122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w3122_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/w3122_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w3_122_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/20/2013 | Customer Initiated Withdrawal | 12/1/2014 | 12/1/2014 |  | S | No
W3-123 | Brandon Shores |  | MD | Unknown | Withdrawn | BGE |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w3123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w3123_imp2.pdf | Interim Study |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w3_123_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/20/2013 | Customer Initiated Withdrawal | 7/26/2011 | 7/26/2011 | 2/29/2012 | S | No
W4-003 | Marengo-Pleasant Valley |  | IL | McHenry | Withdrawn | ComEd | 164 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2010 | N/A | N/A |  | 11/28/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X1-015 | Kenney-Rock Springs 500kV |  | MD | Cecil | Withdrawn | NAEA | 360 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x1015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x1015_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 8/21/2013 | Customer Initiated Withdrawal | 7/1/2013 |  |  | S | No
X1-078 | Deans (Poseidon) 500kV | Poseidon | NJ | Middlesex | Withdrawn | PSEG | 525 |  |  |  | Energy | Merchant Transmission |  | DC | F/TWR 525 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x1078_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x1078_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/x1_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/x1_078_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 4/23/2018 |  | 5/1/2020 | 5/1/2020 |  | S | No
X2-009 | Cedar Grove-Clifton 230kV |  | VA | Fairfax | Withdrawn | PSEG | 206 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x2009_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x2009_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/17/2011 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X2-029 | Danville-East Danville 138kV |  | VA | Pittsylvania | Withdrawn | AEP | 55 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x2029_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 8/7/2014 | Customer Initiated Withdrawal | 1/30/2014 | 1/30/2014 |  | S | No
X2-055 | Cedar Grove-Clifton "B" 230kV |  | VA | Fairfax | Withdrawn | PSEG | 206 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x2055_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x2055_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X3-028 | X3-028 Sullivan 345 kV |  | IN | Sullivan | Withdrawn | AEP | 3500 |  |  |  | Energy | Merchant Transmission |  | DC | FTIR 1500; NFTIR 2000 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x3028_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/30/2011 | N/A | N/A |  | 9/30/2019 |  | 12/31/2016 |  |  | S | No
X3-037 | Krendale-Seneca 138kV |  | OH | Richland | Withdrawn | APS | 46 |  |  |  | Energy | Merchant Transmission |  |  | AC | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3037_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 8/14/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-064 | Fredericksburg-Mine Road 230kV |  | VA | City of Fredericksburg | Withdrawn | Dominion | 237 | 237 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3064_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x3064_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 10/12/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-065 | Bristers-Ox 500kV |  | VA | Fauquier | Withdrawn | Dominion | 183 | 183 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3065_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x3065_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 10/12/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X4-013 | Pleasant View-Edwards Ferry 230kV |  | VA | Prince William | Withdrawn | Dominion | 200 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4013_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x4013_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 11/28/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
X4-022 | Mount Storm 230kV |  | WV | Grant | Withdrawn | Dominion | 358 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 5/30/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X4-023 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 155 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x4023_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/x4_023_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 3/28/2014 |  | 6/1/2015 |  |  | S | No
X4-024 | Rock Springs 500kV |  | MD | Cecil | Withdrawn | NAEA | 109 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4024_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x4024_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 8/21/2013 | Customer Initiated Withdrawal | 7/1/2013 |  |  | S | No
Y1-021 | Fredericksburg-Cranes Corner 230kV |  | VA | City of Fredericksburg | Withdrawn | Dominion | 64 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 3/28/2012 |  | 6/1/2013 |  |  | S | No
Y2-093 | Easton-Easton Tap 69kV |  | PA | Northampton | Withdrawn | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 12/7/2012 | Queue Not Required | 6/1/2013 |  |  | S | No
Y3-030 | Sandy Springs-High Ridge 230kV |  | MD | Unknown | Withdrawn | BGE | 127 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3030_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3030_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/4/2013 | N/A | N/A |  | 4/3/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
Y3-093 | Erie West 345kV |  | PA | Erie | Withdrawn | PENELEC | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 1000; F/TWR 1000 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3093_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/26/2013 | N/A | N/A |  | 10/9/2013 | Customer Initiated Withdrawal | 1/1/2017 | 1/1/2017 |  | S | No
Y3-112 | Butler-Shanor Manor 138kV |  | PA | Armstrong | Withdrawn | APS | 43 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3112_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 4/25/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | S | No
Z1-001 | Blairsville East-Social Hall 138kV |  | PA | Westmoreland | Withdrawn | APS | 15.7 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/2/2013 | N/A | N/A |  | 9/3/2013 | Customer Initiated Withdrawal | 12/31/2014 |  |  | S | No
Z1-004 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2013 | N/A | N/A |  | 5/14/2013 | Queue Not Required |  |  |  | S | No
Z1-016 | Hanna-Juniper 345kV |  | OH | Portage | Withdrawn | ComEd | 140 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2013 | N/A | N/A |  | 6/13/2013 | Queue Not Required |  |  |  | S | No
Z1-017 | Limerick-Peach Bottom |  | PA | Montgomery | Withdrawn | PECO | 181 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2013 | N/A | N/A |  | 2/20/2014 | Customer Milestone Not Met | 6/1/2014 |  |  | S | No
Z1-031 | Lake Nelson-Middlesex 230kV |  | NJ | Unknown | Withdrawn | JCPL | 56 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1031_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/25/2013 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 7/31/2014 |  |  | S | No
Z1-033 | Hudson 230kV |  | NJ | Unknown | Withdrawn | PSEG | 400 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 400; F/TWR 410 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/2/2013 | N/A | N/A |  | 12/18/2013 | Customer Initiated Withdrawal | 10/30/2017 |  |  | S | No
Z1-037 | Krendale-Shanor Manor 138kV |  | PA | Butler | Withdrawn | APS | 43 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/25/2013 | N/A | N/A |  | 5/6/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | S | No
Z1-054 | Byron-Cherry Valley |  | IL | Ogle | Withdrawn | ComEd | 26 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1054_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2013 | N/A | N/A |  | 4/9/2015 | Customer Initiated Withdrawal | 9/30/2014 |  |  | S | No
Z2-016 | Blairsville-Social Hall 138kV |  | PA | Westmoreland | Withdrawn | PENELEC | 15.7 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z2016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | S | No
Z2-018 | South Canton-Harmon 345kV |  | OH | Unknown | Withdrawn | ATSI | 82 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2014 | N/A | N/A |  | 4/21/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
Z2-045 | Cedar Grove-Roseland 230kV |  | NJ | Unknown | Withdrawn | PSEG | 42 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-047 | Steel City 230kV |  | PA | Northampton | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2014 | N/A | N/A |  | 6/9/2014 | Customer Initiated Withdrawal | 7/1/2014 |  |  | S | No
Z2-049 | Cedar Grove-Williams 230kV |  | NJ | Unknown | Withdrawn | PSEG | 21 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-050 | Easton-Trappe Tap 69kV |  | MD | Talbot | Withdrawn | DPL | 13 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-051 | Red Lion-Cedar Creek 230kV |  | DE | New Castle | Withdrawn | DPL | 83 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-052 | Preston-Tanyard 69kV |  | MD | Caroline | Withdrawn | DPL | 20 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-054 | Roseland-Williams 230kV |  | NJ | Unknown | Withdrawn | PSEG | 44 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-055 | Cedar Grove-Clifton 230kV |  | NJ | Unknown | Withdrawn | PSEG | 42 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-061 | Spurlock-Zimmer 345kV |  | KY | Mason | Withdrawn | DEOK | 88 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2014 | N/A | N/A |  | 4/1/2014 |  |  |  |  | S | No
Z2-070 | Worcester-Ocean Pines 69kV |  | MD | Worcester | Withdrawn | DPL | 25 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
Z2-071 | Piney Grove-New Church 138kV |  | MD | Wicomico | Withdrawn | DPL | 55 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
Z2-079 | Pleasant View - Edwards Ferry 230kV |  | VA | Loudoun | Withdrawn | Dominion | 31 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/25/2014 | N/A | N/A |  | 9/8/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA1-029 | Carson Rawlings 500kV |  | VA | Brunswick | Withdrawn | Dominion | 315 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2014 | N/A | N/A |  | 9/8/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA1-030 | Zion-Zion Energy Center |  | IL | Lake | Withdrawn | ComEd | 133 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2014 | N/A | N/A |  | 4/3/2015 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA1-039 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1039_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2014 | N/A | N/A |  | 3/30/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AA1-087 | Timblin-Trade City 115kV |  | PA | Jefferson | Withdrawn | PENELEC | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/12/2015 | Customer Milestone Not Met | 6/1/2016 | 6/1/2016 |  | S | No
AA1-088 | USAP-Woodville 138kV |  | PA | Allegheny | Withdrawn | DL | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/11/2015 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
AA1-089 | Dravosburg-W Mifflin |  | PA | Allegheny | Withdrawn | DL | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1089_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/11/2015 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
AA1-147 | Marion 345kV |  | NJ | Camden | Withdrawn | PSEG | 400 |  |  |  | Energy | Merchant Transmission |  | AC | TWR/400 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/1/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA2-041 | Tidd-Collier |  | OH | Jefferson | Withdrawn | AEP | 225 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 3/16/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AA2-042 | Conastone-Northwest 230kV |  | MD | Harford | Withdrawn | BGE | 102 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa2042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 9/21/2015 |  | 6/1/2016 |  |  | S | No
AA2-108 | Plano 765kV |  | IL | Kendall | Withdrawn | ComEd | 2060 |  |  |  | Energy | Merchant Transmission |  | DC | 2060 FTIR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa2108_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 10/26/2015 | Customer Milestone Not Met | 9/30/2021 |  |  | S | No
AB1-019 | Newlinville 230 kV |  | PA | Chester | Withdrawn | PECO | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1019_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/ab1019_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2015 | N/A | N/A |  | 4/12/2018 |  | 6/1/2018 |  |  | S | No
AB1-024 | Loretto-Wilton Ctr |  | IL | Livingston | Withdrawn | ComEd | 50 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2015 | N/A | N/A |  | 8/25/2016 |  | 6/1/2017 |  |  | S | No
AB1-029 | Loretto-Pontiac |  | IL | Livingston | Withdrawn | ComEd | 35 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2015 | N/A | N/A |  | 3/10/2017 |  | 6/1/2017 |  |  | S | No
AB1-060 | Cloverdale-Jacksons Ferry 765kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-061 | Fieldale-Thornton-Franklin 138kV & Danville-East Danville 138kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-062 | Graceton-Safe Harbor |  | N/A | N/A | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-101 | Cloverdale-Jacksons Ferry 765kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1101_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-102 | Graceton-Safe Harbor 230kV |  | N/A | N/A | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1102_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-103 | Fieldale-Thornton & Danville-E. Danville 138kV | CMN | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1103_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-121 | Byron 345kV |  | IL | Ogle | Withdrawn | ComEd | 1927 |  |  |  | Energy | Merchant Transmission |  | DC | FTIR 989/NFTIR 938 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ab1121_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 6/30/2017 |  | 12/1/2021 |  |  | S | No
AC1-005 | Zion-Stateline |  | IL | Cook | Withdrawn | ComEd | 1000 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2016 | N/A | N/A |  | 6/6/2016 |  | 12/31/2021 |  |  | S | No
AD2-121 | Oyster Creek 230 kV I |  | NJ | Ocean | Withdrawn | JCPL | 530 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/11/2018 |  | 6/1/2024 |  |  | S | No
AD2-122 | Oyster Creek 230 kV II |  | NJ | Ocean | Withdrawn | JCPL | 635 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/11/2018 |  | 6/1/2024 |  |  | S | No
AE1-049 | Tanners Creek - Miami Fort Upgrade Acceleration (b2828; b2831; b2968) |  | OH | Adams | Withdrawn | DEOK |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2018 | N/A | N/A |  | 10/31/2018 |  |  |  |  | EE | No
AE1-234 | Nottingham 230kV Reactor Bypass |  | PA | Chester | Withdrawn | PECO | 578 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Issued |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/2/2018 |  |  |  |  | EE | No
AE1-253 | Tidd-Collier 345kV |  | PA | Adams | Withdrawn | APS | 50 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 11/1/2018 |  | 5/31/2020 |  |  | EE | No
AE2-158 | Kanawha River 138 kV |  | WV | Fayette | Withdrawn | AEP | 48 |  |  |  | Energy | Merchant Transmission | Hydro | AC | 48 NFTIR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 4/1/2019 |  | 10/1/2021 |  |  | S | No
AE2-239 | Tanners Creek-East Bend & Miami Fort-Terminal 345 kV |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 4/1/2019 |  | 3/1/2023 |  |  | S | No
G07_MTX1 | Sayreville 230kV | Neptune | NJ | Middlesex | In Service | JCPL | 790 | 790 |  |  | Energy | Merchant Transmission |  | DC | F/TWR 685; NF/TWR 105 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g07_mtx1_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g07_mtx1_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/g07_mtx1_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/g07_mtx1_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/g07_mtx1_csa.pdf | Document Posted | N/A | N/A |  | 3/8/2001 | N/A | N/A | 1/4/2007 |  |  | 6/30/2007 |  | 6/30/2007 | S | No
G22_MTX5 | Linden 230kV | Linden VFT | NJ | Union | In Service | PSEG | 330 | 330 | 330 |  | Capacity | Merchant Transmission |  | AC | TWR 330 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g22_mtx5_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g22_mtx5_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/g22_mtx5_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/g22_mtx5_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/g22_mtx5_csa.pdf | Document Posted | N/A | N/A | 6/1/2009 | 6/2/2001 | N/A | N/A | 9/16/2009 |  |  | 11/1/2009 | 11/1/2009 | 11/1/2009 | S | No
J02_MTX13 | Keeney XFMR 230/138kV | Keeney Autotransformer AT20 | DE | New Castle | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/j02_mtx13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/j02_mtx13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/j02_mtx13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/16/2002 | N/A | N/A |  | 12/8/2003 |  | 5/31/2003 |  | 5/31/2003 | S | No
J07_MTX12 | Cheswold XFMR 138/69kV |  | DE | Kent | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/j07_mtx12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/j07_mtx12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/j07_mtx12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2002 | N/A | N/A |  |  |  | 12/31/2003 |  | 12/31/2003 | S | No
M05 | Black Oak - Bedington | Black Oak - Bedington Wave Traps 500kV | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/m05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/m05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/m05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/5/2004 | N/A | N/A |  |  |  | 12/31/2005 |  | 12/31/2005 | S | No
O16 | Chichester-Linwood 230kV | FPL Energy Markus Hook | PA | Delaware | In Service | PECO | 230 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/o16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/o16_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2005 | N/A | N/A |  |  |  | 6/19/2005 |  | 6/19/2005 | S | No
O66 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | PSEG | 670 | 670 | 320 |  | Capacity | Merchant Transmission |  | DC | NF/TWR 320/NFTWR 673 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o66_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o66_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/o66_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/o66_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/o66_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2005 | N/A | N/A | 4/4/2013 |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
P31 | Bath County |  | VA | Highland | In Service | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p31_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/p31_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/p31_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/p31_csa.pdf | Document Posted | N/A | N/A |  | 12/5/2005 | N/A | N/A |  |  |  | 12/1/2008 | 12/1/2008 | 12/1/2008 | S | No
R12 | Bedington - Nipetown |  | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/r12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/r12_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/r12_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2006 | N/A | N/A |  |  |  | 4/4/2008 | 4/4/2008 | 6/1/2008 | S | No
U2-028 | Meadow Brook Capacitor |  | VA | Frederick | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IARR 64.5 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/u2028_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/u2_028_csa.pdf | Document Posted | N/A | N/A |  | 5/30/2008 | N/A | N/A |  |  |  | 10/26/2009 | 10/26/2009 | 6/1/2009 | S | No
U2-077 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 300 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 300; NF/TWR 330 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/u2_077_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/25/2008 | N/A | N/A |  |  |  | 10/1/2009 |  | 6/1/2011 | S | No
V1-034 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | PSEG | 673 | 3 | 0 |  | Energy | Merchant Transmission |  | DC | NF/TWR 673 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v1034_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/v1034_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/v1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/v1_034_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2009 | N/A | N/A |  |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
W1-001 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 15 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 15 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/w1_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/2/2010 | N/A | N/A |  |  |  | 3/31/2010 |  | 6/1/2011 | S | No
W1-078 | Sammis-Wylie Ridge 345kV |  | OH | Jefferson | In Service | APS |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1078_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w1_078_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 5/30/2012 | S | No
W2-038 | East Frankfort-Crete | Powerton – Joliet SPS | IL | Will | In Service | ComEd | 800 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w2038_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w2_038_csa.pdf | Document Posted | N/A | N/A |  | 6/22/2010 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 10/5/2011 | S | No
Y1-082 | Longwood-Wye Mills 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y1082_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y1082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y1_082_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 5/2/2016 | S | No
Y3-082 | Easton-Trappe Tap 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3082_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y3_082_csa.pdf | Document Posted | N/A | N/A |  | 4/19/2013 | N/A | N/A |  |  |  | 6/1/2014 |  | 1/29/2016 | S | No
Z2-017 | Bristers Ox 500kV |  | VA | Unknown | In Service | Dominion | 237 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 733 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z2017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z2017_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/z2_017_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 3/25/2015 | S | No
AA2-054 | Pumphrey 230kV |  | MD | Anne Arundel | In Service | BGE | 155 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 65.7 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa2054_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/aa2_054_csa.pdf | Document Posted | N/A | N/A |  | 2/23/2015 | N/A | N/A |  |  |  | 1/1/2016 |  | 6/7/2017 | S | No
AB2-020 | Roseland-Williams 230kV |  | N/A | N/A | In Service | PSEG | 40 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 62 | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab2020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/ab2020_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/ab2_020_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 11/22/2017 | S | No
AB2-021 | Keeney-Rock Springs 500kV |  | MD | Unknown | In Service | Essential Power | 100 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 705 | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab2021_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/ab2021_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/ab2_021_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 10/31/2018 | S | No
Y3-064 | Pierce-Beckjord 138kV |  | OH | Clermont | Engineering and Procurement | DEOK | 160 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 155 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3064_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3064_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y3_064_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2013 | N/A | N/A |  |  |  | 4/3/2019 | 4/3/2019 |  | S | No
Y3-092 | Erie West 345kV | ITC Lake Erie Connector | PA | Erie | Engineering and Procurement | PENELEC | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 1000; NF/TWR 1000 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/y3_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y3_092_csa.pdf | Document Posted | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 3/31/2024 | 3/31/2024 |  | S | No
AB2-019 | Erie West 345kV |  | N/A | N/A | Active | PENELEC | 28 |  |  |  | Energy | Merchant Transmission |  | DC | 28 FTWR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ab2019_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | S | No
AD2-083 | Larrabee 230kV |  | NJ | Monmouth | Active | JCPL | 1100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ad2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ad2083_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AD2-084 | Cardiff 230kV |  | NJ | Atlantic | Active | AEC | 1100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ad2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ad2084_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AE1-037 | Deans 500kV |  | NJ | Middlesex | Active | PSEG | 1200 | 1200 | 1200 |  | Capacity | Merchant Transmission | Wind | AC | 0 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ae1037_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/18/2018 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AE1-077 | Sandy Springs-High Ridge 230 kV |  | MD | Allegany | Active | BGE | 100 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ae1077_imp-arr.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | EE | No
AE2-009 | Nottingham-Peach Bottom Tap 230 kV line |  | PA | Adams | Active | PECO | 11 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | EE | No
AE2-014 | Sewaren 230 kV |  | NJ | Middlesex | Active | PSEG | 1200 | 1200 | 1200 |  | Capacity | Merchant Transmission | Wind | DC | 1200 F/NF TIR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ae2014_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2018 | N/A | N/A |  |  |  | 1/1/2024 |  |  | S | No
AE2-240 | Olive-Reynolds 1 & 2 345 kV |  | IN | Starke | Active | AEP | 3170 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 6/1/2019 |  |  | S | No
AF1-025 | Cedar Creek-Silver Run 230 kV |  | DE | New Castle | Active | DPL | 50 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Not Required |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2019 | N/A | N/A |  |  |  | 5/31/2020 |  |  | EE | No
AF1-088 | Sullivan 345 kV |  | IL | Clark | Active | AEP | 1000 | 1000 | 1000 |  | Capacity | Merchant Transmission |  |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AF1-200 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 2035 | 0 |  |  | Energy | Merchant Transmission |  | DC | 0 | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 1/31/2025 |  |  | S | No
AF2-008 | Sullivan 345 kV |  | IL | Clark | Active | AEP | 3500 | 2500 | 500 |  | Capacity | Merchant Transmission |  | DC | 0 | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/3/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AF2-015 | Essex-McCarter 230 kV |  | NJ | Essex | Active | PSEG | 50 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2019 | N/A | N/A |  |  |  | 7/1/2021 |  |  | EE | No
AF2-028 | Pumphrey 69 kV |  | MD | Baltimore County | Active | BGE |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Issued |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A | [6 empty] | EE | No

## Definitions-Mapping
Column Names from Data Tab
Queue | Queue/OASIS Number
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the queue position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection queue process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Queue Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Queue
Sliding Queue