## Data
Queue Number | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim Interconnection Service Agreement | Interim/Interconnection Service Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Queue Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Projected In Service Date | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Queue | Sliding Queue
S07 | Keystone-Branchburg | AC Landfill Energy Units 1, 2, 3 | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s07_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s07_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s07_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S08 | Kammer-Doubs |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s08_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s08_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s08_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S09 | Conemaugh-Conastone |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s09_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s09_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s09_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S10 | Jacksons Ferry-Burches Hill |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s10_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s10_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s10_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
T176 | Juniata-Branchburg |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T177 | Belmont-Brighton |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T178 | Keystone-Juniata |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
V3-052 | NI HUB-DC Cook |  | N/A | N/A | In Service | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v3052_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v3052_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v3052_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/21/2009 | N/A | N/A |  |  |  | 2/1/2013 | 2/1/2013 |  | EE | No
V4-006 | Byron 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4006_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4006_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4006_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 2/18/2012 |  |  | EE | No
V4-007 | Quad City 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4007_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4007_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4007_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-008 | Braidwood 1-AD Hub | Suburban Landfill | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4008_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2009 | N/A | N/A |  | 2/15/2012 |  |  |  |  | EE | No
V4-030 | Byron 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4030_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4030_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4030_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-031 | Quad 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4031_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4031_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4031_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
W3-065 | Braidwood-Cook |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/w3065_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2010 | N/A | N/A |  | 4/4/2013 |  |  |  |  | EE | No
X4-033 | Braid 24kV BR-1-Cook 765kV |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2012 | N/A | N/A |  | 11/12/2012 |  |  |  |  | EE | No
X4-036 | Braidwood-Cook |  | N/A | N/A | Withdrawn | ComEd | 250 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/x4036_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 9/3/2014 |  |  |  |  | EE | No
X4-037 | Dresden-DEOK Zone |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/x4037_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 9/3/2014 |  |  |  |  | EE | No
X4-038 | TMI-PPL |  | N/A | N/A | Withdrawn | PPL | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/x4038_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/x4038_arr-fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 11/18/2014 |  |  |  |  | EE | No
Y2-047 | Peach Bottom-BGE |  | N/A | N/A | Withdrawn | PECO | 200 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/y2047_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2012 | N/A | N/A |  | 7/15/2015 |  | 1/1/2013 |  |  | EE | No
Y2-094 | 4 Quad Cities-1-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 250 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/y2094_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Z1-006 | NIPSCO-BOCGASE2 |  | N/A | N/A | Withdrawn | AEP | 25 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [5 empty] | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2014 | N/A | N/A |  | 5/29/2015 |  |  |  |  | EE | No
Z1-083 | Salem Unit 1-PSEG Zone |  | NJ | Salem | Withdrawn | PSEG | 300 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z1083_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 9/2/2015 |  |  |  |  | EE | No
Z1-084 | Quad Cities 1-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 475 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z1084_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Z1-085 | Quad Cities 2-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 525 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z1085_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Z2-053 | Bridgewater-S. River |  | N/A | N/A | Withdrawn | PSEG | 156.1 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z2053_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-069 | Bridgewater-Hoboken |  | N/A | N/A | Withdrawn | PSEG | 105 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z2069_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-072 | Indian River-New Church |  | N/A | N/A | Withdrawn | DPL | 204.6 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z2072_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
AA1-035 | Edgecomb-Roanoke Valley |  | N/A | N/A | Withdrawn | Dominion | 60 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1035_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/1/2014 | N/A | N/A |  | 3/31/2016 |  |  |  |  | EE | No
AA1-090 | Cheswick 24kV Unit 1-AEP-Dayton HUB |  | N/A | N/A | Withdrawn | DL | 565 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1090_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 5/25/2016 |  |  |  |  | EE | No
AA1-119 | Sunset Lake-Mardela |  | N/A | N/A | Withdrawn | DPL | 139 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1119_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/30/2017 |  |  |  |  | EE | No
AA1-120 | Fowler-LaPorte |  | N/A | N/A | Withdrawn | AEP | 64 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1120_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 11/8/2017 |  |  |  |  | EE | No
AA2-172 | ATSI-PSEG |  | N/A | N/A | Withdrawn | PSEG | 115 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/8/2015 |  |  |  |  | EE | No
AB1-031A | LAKEWOOD 18 KV OCEAN C1-ATLANTIC 230 KV REACTR |  | NJ | Unknown | Withdrawn | JCPL | 25 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ab1031a_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2015 | N/A | N/A |  | 3/3/2017 |  |  |  |  | EE | No
AB1-185 | 4 QUAD C18 KV QC-1-981 CRES 138KV PROVIDWF |  | N/A | N/A | Withdrawn | ComEd | 2 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ab1185_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2015 | N/A | N/A |  | 10/18/2018 |  | 6/1/2016 |  |  | EE | No
AB1-186 | REDLION 34.5 KV REDLINFC-KENT 13 KV DOVER2CT |  | N/A | N/A | Withdrawn | DPL | 3 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ab1186_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2015 | N/A | N/A |  | 11/26/2018 |  | 6/1/2016 |  |  | EE | No
AC1-192 | Conastone-Peach Bottom-N/A |  | N/A | N/A | Withdrawn | PECO |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/2/2016 |  |  |  |  | EE | No
AC1-223 | E. Frankfort-Universit-N/A |  | IL | Will | In Service | ComEd | 43.2 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ac1223_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/ac1223_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/ac1223_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 |  | 12/12/2018 | EE | No
AC2-032 | Graceton-Cooper 230kV-N/A |  | N/A | N/A | Withdrawn | BGE | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/3/2017 |  | 6/1/2018 |  |  | EE | No
AC2-033 | Graceton-Bagley 230kV-N/A |  | N/A | N/A | Withdrawn | BGE | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/24/2017 |  |  |  |  | EE | No
AC2-034 | Eugene-Dequine 345kV-N/A |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 3/24/2017 |  |  |  |  | EE | No
AC2-065 | Delaware-Darby 138kV-N/A |  | N/A | N/A | Withdrawn | Dayton | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 5/24/2017 |  | 6/1/2018 |  |  | EE | No
AD1-014 | Hutching-Sugar Creek 138k-N/A |  | N/A | N/A | Withdrawn | Dayton | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 4/17/2017 | N/A | N/A |  | 5/24/2017 |  | 6/1/2018 |  |  | EE | No
AD1-086 | E. Frankfort-Goodings Grove |  | IL | Will | Active | ComEd | 23.9 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ad1086_arr-imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2017 | N/A | N/A |  |  |  | 6/20/2021 | 6/20/2021 |  | EE | No
AD2-018 | Roseland-Cedar Grove |  | NJ | Unknown | Engineering and Procurement | PSEG | 248 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ad2018_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/ad2018_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/ad2_018_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 |  | EE | No
AD2-019 | Williams-Cedar Grove |  | NJ | Unknown | Engineering and Procurement | PSEG | 1399 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ad2019_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/ad2019_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/ad2_019_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 |  | EE | No
AD2-053 | South Canton-Harmon 345kV |  | OH | Adams | Withdrawn | AEP | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2018 | N/A | N/A |  | 9/19/2018 |  | 6/1/2019 |  |  | EE | No
AD2-054 | Dumont-Stillwell 345kV |  | IN | St. Joseph | Withdrawn | AEP | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2018 | N/A | N/A |  | 5/2/2019 |  |  |  |  | EE | No
AD2-080 | Stillwell 345kv-Dumont 345kV |  | IN | St. Joseph | Active | AEP | 309 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | EE | No
AE1-078 | Greendale-Miami Fort |  | OH | Adams | Withdrawn | DEOK | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ae1078_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  | 9/23/2019 |  | 6/1/2020 |  |  | EE | No
AE1-184 | Pontiac Midpoint-Dresden |  | IL | Livingston | Active | ComEd | 82.7 | 82.7 |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | EE | No
AE2-032 | Pnode 1369011078-Pnode 51299 |  | PA | Lackawanna | Withdrawn | PPL | 811 | 811 |  |  | Energy | Upgrade Request |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-feas_docs/ae2032_arr-fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2019 | N/A | N/A |  | 9/5/2019 |  |  |  |  | EE | No

## Definitions-Mapping
Column Names from Data Tab
Queue | Queue/OASIS Number
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the queue position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection queue process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Queue Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Queue
Sliding Queue